## Budget follow-up
Project name: | Project duration: 24 months |  |  |  |  | Cells with formulas have been locked to avoid accidental breakage of formulas :) password to open excel is 'password'
| Updated | 2018-01-01
Budget follow-up tool | [5 empty] | Budget realized
Staff |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Project Manager (50% of salary) |  |  |  | 40000 | 30000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000
Financial manager |  |  |  | 20000 | 15000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
Project person 1 |  |  |  | 30000 | 22500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500
Project person 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project person 18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project person 19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 90000 | 67500 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 22500
Travel and accomodation |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Kick off meeting |  |  |  | 2500 | -400 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 2900
Partner meeting 2 |  |  |  | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dissemination event/seminar |  |  |  | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 9000 | 6100 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 2900
External expertise |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Roll-ups |  |  |  | 500 | 100 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400
Marketing materials |  |  |  | 900 | 150 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 750
Catering in partner meeting |  |  |  | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 2600 | 1450 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 1150
Equipment |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Laptop |  |  |  | 1500 | -220 | 0 | 1720 | 0 | 0 | 0 | 0 | 0 | 1720
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 1500 | -220 | 0 | 1720 | 0 | 0 | 0 | 0 | 0 | 1720
Infrasturcture and works |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flatrate (15% of staff costs) |  |  |  | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Flatrate total |  |  |  | 13500 | 10125 | 0 | 3375 | 0 | 0 | 0 | 0 | 0 | 3375
ERDF funding / Own funding |  | 75% | 25%
Budget total | TOTAL BUDGET | ERDF funding | Own funding |  | Budget left total | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Staff | 90000 | 67500 | 22500 |  | 67500 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 22500
Travel and accomodation | 9000 | 6750 | 2250 |  | 6100 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 2900
External expertise | 2600 | 1950 | 650 |  | 1450 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 1150
Equipment | 1500 | 1125 | 375 |  | -220 | 0 | 1720 | 0 | 0 | 0 | 0 | 0 | 1720
Infrasturcture and works | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flatrate (15% of staff costs) | 13500 | 10125 | 3375 |  | 10125 | 0 | 3375 | 0 | 0 | 0 | 0 | 0 | 3375
TOTAL BUDGET | 116600 | 87450 | 29150 |  | 84955 | 0 | 31645 | 0 | 0 | 0 | 0 | 0 | 31645
Budget used | 27.14%

## Instructions
Staff | TOTAL BUDGET | Budget left | Period 0 (Preparation) | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Total expenditure
Project Manager | 50000 | 18000 | 0 | 8000 | 8000 | 8000 | 8000 | 0 | 0 | 32000
Financial manager | 40000 | 27500 | 0 | 2500 | 2500 | 2500 | 5000 | 0 | 0 | 12500
Project person 1 | 25000 | -2000 | 0 | 6000 | 6000 | 7000 | 8000 | 0 | 0 | 27000
Project person 2 | 20000 | 10000 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 10000
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 135000 | 53500 | 0 | 19000 | 19000 | 20000 | 23500 | 0 | 0 | 81500
Instructions • Fill in your project budget in column E for all budget lines and sub-budget lines. (Simple example above with staff costs) • Update expenditure to the right side of the black bar. Do this at least after every period (Preferably more often) to keep track of your projects budget. Feel free to pass this excel to your partners as well should they need it. • All cells with formulas have been protected to avoid accidental breakage of the table. If you need to modify the table simply unprotect the table, password is ‘password’